## Sheet1
MindMaster Action Plan:
Project Scope: MindMaster Module 1: Psychology Literacy for Primary Grade 1 Duration: January – December 2026 Development Model: Rapid Application Development (RAD) Primary Goal: Deploy and validate the full solution of MindMaster’s Grade 1 module as a child-centric, AI-powered psychology literacy tool through iterative, user-driven development.
2026 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Phase 1: Curriculum Roadmap (Grade 1–6) & Content Development (Grade 1) (Month 1-2)
Objective: Design a coherent, developmentally appropriate Psychology Literacy Curriculum roadmap for Grades 1–6, and fully develop the learning and assessment content for Grade 1. This curriculum will directly inform platform features and guide prototype development in Phase 2.
1) Define core competencies and progression themes for Grades 1–6 in psychology literacy. | x
Develop Levels 1 & 2 content focused on foundational literacy (Alphabetical Literacy).
Establish a universal literacy framework and culturally adaptive content guidelines.
evelop interactive lesson structures integrating phonemic awareness, phonics, vocabulary, and comprehension.
2) Develop a structured curriculum roadmap outlining learning outcomes by grade. | x
Design and implement AI-generated Learning Assessment Tools for level placement and pre/post assessments.
Develop the user interface, including:
Lesson mapping and learning path interface.
Real-time performance monitoring dashboard
Achievement board, day streak feature, and level completion certificates.
3) Create full Grade 1 content including lessons, activities, journaling, and formative assessments. | x | x
Create real-time student performance tracking tools and class-level summary reports.
Develop downloadable resources (unit objectives, expected learning outcomes, instructional guides).
Provide professional development resources for teachers.
4) Prepare content formats for integration with chatbot, adaptive pacing, and offline features. |  | x
5) Finalise Prototype Pilot site selection (2–4 learning centres) and obtain consent from partners and participants. |  | x
Phase 2: Prototype Development & Pilot - Isolated Feature Validation (Months 2-6)
Objective: Rapidly build and iteratively test key MindMaster components (e.g. AI chatbot, journaling tool, adaptive model, offline sync) to validate usability, technical functionality, and learner engagement. Use real-time feedback from children and facilitators in non-formal settings to refine individual features before full integration.
1) Develop functional prototypes for AI chatbot, journaling tool, and adaptive pacing engine. | x | x | x
2) Build and test offline deployment and basic teacher dashboard features. |  |  | x | x | x
3) Conduct iterative field-testing of individual features with children and facilitators at selected learning centres. |  |  | x | x | x
4) Collect feedback through weekly check-ins, facilitator interviews, and child reflection prompts. |  |  | x | x | x
5) Refine features based on real-time usability, engagement, and technical performance data. |  |  |  |  | x | x
6) Finalise integrated feature bundle and content modules for full pilot implementation. | [5 empty] | x
Phase 3: Full Solution Pilot (Month 7-11)
Objective: Deploy the fully integrated MindMaster Module 1 with Grade 1 learners through a staggered pilot roll-out—in formal schools (June–October) and non-formal learning centres (July–November)—to evaluate learning outcomes, user experience, and system readiness at scale. Use mixed-method data (quantitative and qualitative) to assess educational impact, technical performance, and cultural relevance, guiding final refinements before consolidation.
1) Onboard 2 formal Thai schools and conduct teacher (facilitator) training. | [5 empty] | x
2) Onboard 3 learning centres and conduct teacher (facilitator) training. | [6 empty] | x
3) Deploy the full Grade 1 MindMaster solution in ten classrooms across pilot sites. | [5 empty] | x | x | x | x | x | x
4) Monitor platform usage and engagement through real-time analytics and observation. | [5 empty] | x | x | x | x | x | x
5) Collect pre- and post-test data to assess learning outcomes and psychological gains. | [5 empty] | x | x |  |  | x | x
6) Conduct structured interviews, surveys, and classroom observations to gather qualitative feedback. | [7 empty] | x | x | x | x
7) Iterate content and UX based on pilot findings to ensure readiness for scale. | [9 empty] | x | x
Phase 4: Evaluation & Consolidation (Month 12)
Objective: Conclude the project with a comprehensive review of pilot outcomes, consolidate learning data, refine the solution, and produce open-access deliverables to support scale-up, replication, or further investment.
1) Analyse pilot data (pre/post test results, usage metrics, qualitative feedback) | [11 empty] | x
2) Refine content and platform based on findings. | [11 empty] | x
3) Prepare final deliverables: - Monitoring, Evaluation and Learning (MEL) report - Public GitHub update (code + documentation) - Recommendations for next-stage implementation | [11 empty] | x
4) Submit final report to UNICEF, aligning with funding compliance. | [11 empty] | x